## EPICs (hidden)
Priority | EPIC Name | Description | Business Justification | Owner | High level Estimation | Comments
1 | Ad Server Upgrade for revenue scaling | 1. Ad Server need to be able to serve 170 m P1/P2 Reqs, 13.5 m Interstitial Impressions. 2. Ad Server needs to be able to run with good stability (Any MTBF requirement?) 3. Ad Server needs to be performance efficient to be able to serve above mentioned ad impressions. 4. Ad Server should integrate more external ad networks to improve revenue improvements. | 27 Lakhs Ad Revenue expected in Oct-Dec timeframe | Shashi
3 | Cool Ads for better Brand attraction | Overall Ad framework of newshunt should start supporting new cool Ads such as 1. Screen Grab Ads, 2. Video Ads, 3. Tall banners etc | (a) 28 Lakhs Ad Revenue expected in Oct-Dec timeframe (b) Better sell of ad framework to brands on ongoing basis | Shashi
8 | Newhunt international Introduction | 1. Newshunt solution needs to be scaled & upgraded for international news papers. 2. Implications of new language support, performance , new client UI needs should be analysed and implemented. | Increase unique users, and subsequently bring more revenues | Ram
12 | NewsHunt Operations Improvements-Fetch Errors | 0 Fetch Errors | Keep the existing end users satisfied to retain them & spread it to new users. Has indirect implication on revenue | Ram

## Features (hidden)
EPIC | Feature | Description | High level Estimation | Comments
Ad Server Upgrade for revenue scaling | Ad Server base OpenX version upgrade to 2.8.7 | 1. Improve ad server maintainability by following OpenX 2.8.7 plugin based architecture. E.g. Future upgrades for the OpenX code should be doable with reasonable effort. 2. Improve ad server performance by removing self XML-RPC calls. 3. Improve ad server maintainability by following well defined build, release process.
| Ad Server performance improvements | 1. Further improvement to performance by removing HTTP self requests in impression logging sequence. 2. This would mean need to sort out the cookie creation/writing issues handled by the internal curl call. 3. Any possibility to improve the memcache calls. (e.g in caching log & click URLs only if needed)
| Inner-active ad network integration | 1. The ad network to be integrated for middle east. 2. Any filters needed to avoid unwanted content? 3. Verify image fetch, click & impression logging sequences are handled properly. 4. Does ad network expect their own impression logging.
| Zest Adz (Komli Media) ad network integration | 1. The ad network to be integrated for middle east. 2. Any filters needed to avoid unwanted content? 3. Verify image fetch, click & impression logging sequences are handled properly. 4. Does ad network expect their own impression logging.
| Ad network hopping to improve overall fill-rate | 1. Ad Selection sequence needs to check if external ad network filled a valid Ad. 2. If not, need to keep switching till valid ad is filled.
Ad Targetting support??? (NOT CLEAR)
Cool Ads for better Brand attraction | Screen Grab Ads support from the Ad server | NOT CLEAR
| Screen Grab Ads support from the Android clients | NOT CLEAR
| Screen Grab Ads support from the iPhone clients | NOT CLEAR
| Screen Grab Ads support from the Symbian clients | NOT CLEAR
| Screen Grab Ads support from the J2ME clients (is it needed?) | NOT CLEAR
Vidopia integration for video ads?
Video ad serving from Eterno Ad Server?
| Tall Banner? | NOT CLEAR
Newhunt international Introduction | X international language support in NewsHunt server | NOT CLEAR
| Y international language support in NewsHunt server | NOT CLEAR
| XYZ international newspaper integration | NOT CLEAR
| Performance & stability check on India & International newshunt solution? | NOT CLEAR
NewsHunt Operations Improvements-Fetch Errors | 0 Fetch Errors | NOT CLEAR

## Product Backlog (hidden)
No | EPIC | Feature | User Story
| Ad Server Upgrade for revenue scaling | Ad Server base OpenX version upgrade to 2.8.7 | Title: As Ad Server lead developer, I would like to upgrade the base OpenX version to 2.8.7. Acceptance Criteria: 1. Eterno additions to the OpenX are moved to plugins based architecture. 2. Well defined configuration management & build & release process is defined. 3. The new code is FuTe tested without any critical errors. 3a. The new code is performance tested without any critical errors. 4. The new code is deployed to the server without affecting the running campaigns and their statistics. 5. The new code is checked into CVS repository. Predecessor: None. Initiated by: Mihir Comments: Estimation:
|  | Ad Server performance improvements | Improve the ad serving time to 60 sec.
|  | Inner-active ad network integration | Integrate inner active Ad network
|  | Zest Adz (Komli Media) ad network integration | Integrate any other Ad network
|  | Ad Server base OpenX version upgrade to 2.8.7 | Remove plugin configuration issues & remove unwanted plugins. E.g. oxMarket
|  | Ad network hopping to improve overall fill-rate | Switch Ad network when empty ad is received.
|  | Ad Server performance improvements | Performance improvement, remove redirection for lg.php call.
|  | Ad Server performance improvements | Performance improvement, remove any unnecessary memcache calls.
|  | Ad Server base OpenX version upgrade to 2.8.7 | Code cleanup.
| Cool Ads for better Brand attraction |  | Screen Grab Ads
Tall Banner
Video Ads
GPS Location based ads?

## Checkins (hidden)
1 | Buzzcity newline at the end removed | Production | Done
2 | resize_external flag in conf file | Production | Done
3 | modifyLongUrl (memcache connect) Logging. LOG.php : Removed the old entry in memcache after use! | Production | Done
4 | Index.php : Logging related changes. | Production | Done
5 | iPAD GIF changes (mobi): showBanner + index.php (getBannerSize) Need to add the ad_position table entries. | Mobi
6 | Disable old cron jobs?
7 | No memcache in click: modifyLongUrl click.php. |  | done
| GICF website ad, clicks not counted |  | done

## Backlog
High Level Target | Description | Status | Comment
5 | Staging setup | Done
6 | New Production setup: - Procedure. | Done | PHP installation issue Memory issue. Fixing REMOTE-ADDR issue.
| New Production setup: - Testing, - Performance verification | Done
8 | Purchasing & updating MaxMind DB. | Done | Update to production, net.in(staging), new prod Accuracy is not good!!!
| Report tool setup on new staging setup | Done
| Old server data backup | Done | Waiting for disk.
| Rich ads implementation | Done | New interest in it.
| Operator specific dummy banners | Done
Performance | LOAD BALANCED SETUP. | Done
Revenue | Inmobi Advanced XML API. - User Agent + IP Address issue | Done
Stability & maintenance | EternoAds disk replacement | Done
Unique Users | Referral program Ads | Done | There were security issues identified which needs to be closed.
Stability & maintenance | New Ad Server Installation, taking care of the scripts | Done | Hang issue with the server. Keep monitoring
Stability & maintenance | WAP Spurious Request Cookie based check | closed | Jay
Revenue | AD NETWORK: Admob, DFP, Ad Exchange Integration (Discussion with Google ) - Issues: Ad doesn't refresh in List some times. - news full story reading affected? - Check alignment (left aligned some times?) | Open | Kausik
Revenue | FEATURE MAJ: Page Insert type of Ads. Create New Ad type. Add news read count configuration. | Done | Arun
Stability & maintenance | Moving Cookie implementation to Clients. Server support needed too! | Done | Jay
Stability & maintenance | Growing Image files : Folder structure based solution. resize_cache cleanup.When banner's main (base) image is changed, the old and its associated resized files don't get deleted.. | Done | Arun
Stability & maintenance | Folder structure based solution. resize_cache cleanup. | Open | Arun
Stability & maintenance | Local File system cache support to keep NFS depenendcy to less | Open | Arun
Stability & maintenance | Fourth delivery server setup, code synergize.. Keep all node code similar. Maintenance script: How to make it easy for Ops? | Done | Jay/Kausik
Revenue | AD NETWORK: External url caching, "--" type url config in admin tool & via external Ad network? Issues is not only with oadest part, but any other parameter separated by "--" | Open | Arun
Stability & maintenance | Some odd cities detected in new MaxMind DB? Are they correct? If yes, from corresponding GPS is it possible to know what are nearest cities? How to change the mapping arrays in GPS delivery limitations? | Open | Jay
Stability & maintenance | Some totally unanswered click numbers? Where else they are seen - what other tables or only one table? How are they entering the system? Can we put some checks in place to avoid them - hash on zoneid,bannerid,clientid & verify the same in click.php--Need to take care of long and short urls? | Open | Jay
Stability & maintenance | Monitoring: Status of m and r files, status of /var space, status of valid-ads, status of cookie-jar write failure? Monitoring: Maintenance failure. Automated daily monitoring of banners getting served + disk space etc. Need to monitor external networks Need a mail | Open | Arun
Stability & maintenance | Cookie Cache failure monitoring, moving cookie from Wowza to Ads3? | Done | Jay
Stability & maintenance | Location look up when memcache failure happens. | Open | Jay
Revenue: | Making html5 set of features more flexible. - (MRAID or ORMMA capabilities?, Flexibility for displaying the ad in various ways: say semi-transparent, diff sizes, Ability to integrate with external networks?) - MRAID Examples. - External Server to Server Integrations. - Bugs and Pending Issues. | Done | One release done.
Revenue | MRAID: Video inline, any performance issues.
Stability & maintenance | MAINTENANCE: Code Checkin, setup on Staging.Keep all node code similar. Maintenance script: How to make it easy for Ops? | Open | Arun
Stability & maintenance | MAINTENANCE: Database Backup and setup of recurring backup! | Open | Arun
Stability & maintenance | Dummy Banner Serving when no Ad is present, this should be done in Ad Selection logic, so that unnecessary impressions are not wasted on dummy banner? Hope it doesn't hamper contract campaign scheduling.e.g. It won't find any banner to serve hence overdelivery should not happen! | Open | Arun
Stability & maintenance | Windows Tablets new zones and image sizes. | Done | Jay
Stability & maintenance | Ads Report tool, new features | Open | Arun
Stability & maintenance | FEATURE: Adding 'wp8' as new platform. | Done | Targeting, report, ad-size, revenue report.
Revenue: | MAINTENANCE: External Ad networks need consistent User Agent Reporting. (Verify and change s-s API integration code snippets) (MID) -- Click.php code updation is requied. | Open | Arun
Revenue: | AD NETWORK: Millenialmedia API | Retired
Revenue: | AD NETWORK: Buzzcity new API? | Hold
Stability & maintenance | MAINTENANCE: Logging not recognised zones+ Are all new papers taken care?, so that UU counts come close to Newshunt | Done | Jay
Stability & maintenance | PNG/JPG creating file sizes which are only required for the given Ad type | Open | Arun
Stability & maintenance | MAINTENANCE: Daily report has WAP statistics, to make it as different table? (LOW): Daily report taking time. | Open | Arun
Revenue | FEATURE MAJ: WAP and Ad Server Integration (Cookie handling, Long url handling not required) + IP->City mapping + client parameter + correct logging (LOW) | Done
Revenue | Cricket dummy paper handling | Done
Revenue | AD NETWORK: External url caching, "--" type url config in admin tool. Any Richmedia Ads? | Open | Arun
Revenue | Smaato Ad Network Integration.
Revenue | AD NETWORK: Adnear integration and issues | Retired
Revenue | Vdopia, Integration | Hold
Stability & maintenance | New Per campaign platform wise reporting needs | Done | Revenue report.
Stability & maintenance | Daily Report problems | Done
Revenue | AD NETWORK: Buzzcity and Inneractive API upgrade, VSERV, Komli, Mojiva, Vdopia. | Hold | Jay
Revenue | FEATURE: External impression tracker configuration | Done | Jay
Revenue | Location Based Targetting: Lat/Long based City selection, Cell-Id to lat/long conversion. Lat/Long vicinity limitation. | Done
Stability & maintenance | FEATURE: Add delivery limitation based on Ad Size selected. | Done
Stability & maintenance | Banner DELETE gives some issue | Open | Kausik
Stability & maintenance | For our own banner types involving additional table ox_banner_lp, duplicate doesn't work! | Open | Kausik | How to do it w/o intervention to OpenX code?
Stability & maintenance | FEATURE MAJ: BSNL LIVE ISSUE: It doesn't like 'ads' keyword in the URL. | Open | Kausik/Arun
Stability & maintenance | FEATURE: Add delivery limitation for App Version Range. | Open
Revenue | FEATURE MAJ: Interstitial Ads to become animated & clickable | FUTURE
Revenue | FEATURE MAJ: Video Ads | FUTURE
Revenue | FEATURE MAJ: Launch Ads (Basic Image, Cool Ad, Basic Image with landing page) | FUTURE
Revenue: | FEATURE MAJ: User Profile based targetting: Ability to categorize banners into major interest categories. Delivery limitation to target ad based end user's ad interest profile. | FUTURE
Stability & maintenance | Cookie Cache operations failing occasionally as it gets full | Retired | Jay
Stability & maintenance | Performance issue debugging: - Cookie Handling done via cache. (via Couchbase in place), need to keep monitoring how it grows & behaves. On high load, it went "down". Needed a restart. - On high load, too many mySql connections. - PhnDb lookup has been issue. - On high load, 600+ acnt, another m/c would be needed? - Memcache pconnect issues. (done via memcache_connect now) - Crash problems. - Zend_mm_heap corrupt. - Still connections get stuck. (45th min problem, there is some mysql lock or something?) - MySql count reduction. - Trying different logging system? - MySql m/c connectivity is lost.? - Live diagnostics? To help detect unknown issues & behavior. - Any other configuration required? - APC new version? - MySql access limiting. (How to increase cache timeout & be able to refresh it whenever required?) - ck.php ? Any changes? - How to limit adnetwork access going out of control? Actually timeout not working? - UI Seperation? | Open | Other: - Reduce logging. - Perf stats logging based on some trigger to find where time is taken - Access log rotation. - Hopping control based on load. - Reduce some more tables. | Try: php.ini: Memory & processing time limt. Etc/hosts: entries? Why connection gets removed after some time : secure. SYC attack: messages log. Mysql connection: persistent/? | >two more golis around KeepAlivec.I think we can switch it off if it is ON in http conf... > > >Finally, KeepAlives will mainly just kill a busy site. Turning them off is recommended now, to avoid just the sort of resource starvation you are seeing regularly. If, for example, you have set 100 MaxClients, and a KeepAlive of 30 seconds, than just 100 visitors within a 30 sec period would hold open all the Apache slots, and you can't serve anything else. KeepAlive Off. > >For your CPU problem I would look at your MaxClients and MaxRequestsPerChild. They could be set too high. Also look at your KeepAliveTimeout setting and make sure it's not to high.
MSISDN | One more way to hit msisdn url using 'ebu' | Retired
New Feature | RIM to be added as new platform: Analyse what all changes required. | Open | Arun
Stability & maintenance | md5 based click urls are not generated properly. | Open | Arun | ??
Stability & maintenance | Client Handset segregation as 'Premium/Regular/low'? Utilising PHNDB Refactoring? | FUTURE
Stability & maintenance | Resolution based limitation, how to make to correct? | Retired
Stability & maintenance | size: Nearest match handling | Done | Jay
| Komli Integration | Done
Stability & maintenance | There are various "banner invalid" "No Ad array" errors in dellog. Why so? Unknown zones? Processing issues? | Open | Jay
NEW: Delivery Limitation | Client Feature based limitation | Done | Client's send Feature flag.
NEW: Ad Networks | Mojiva Integration? | Done
Revenue: Ad Networks | Inneractive Full screen Wait Ads? | FUTURE
| Wait ads add capping. (+ always on dummy banner will have to be there to know capacity) | Done
| Higher size than 300x50 for iPhone 4S and Android Note. | Done
7 | Report table issue | Done | Ok for now.
| Location Targetting | Done
Admin UI | Ability to bulk select 'Premium/Regular/Wait' zones. | Done
Stability & maintenance | CODE CLEANUP:Remove unwanted files & functions. Code formatting? Consolidate functions to few files if that makes sense. | Open | Kausik
Documentation | API documentation | Open | Shashi
Documentation | User Guide. | Open | Ramjee
Documentation | Design Documentation: - Code Arrangement. - Plugins. - Hooks - DB Additions. - Load Balancing, what rules - Ad Types: Cool Ad, Form Popups etc. - Installation guideline, cron jobs. - List of all tools, reports etc. - Misc: Migration Guide for 2.8.7 Version | Open | Shashi

## Errors
| inde9.php getting hit? | Too many errors like that.
3
| memcache default entry problem? | Temporarily avoided by not storing default entry for adsize.
2 | "__" in the click URLs cause problem?
4 | logNhRequest doesn't capture all requests, do some have field limit exceeded? Empty field?

## SmallerItemChecklist
Description | Status | Comment
Idea Heaven Campaign | Done
Helios Mumbai Campaign | Done
Campaign Analysis & fixing problems. | Done | 4th Apr changes done. 5th Apr: Microsoft made exclusive.
New Campaign (ICICI) iphone/ipad wap link | Partial | J2ME issue/Android issue
Analyse Microsoft Logs | Done
IBM Campaign | Done | Paused?
Shreya region wise Nokia numbers | Done
checkins | Open
External network country wise tuning. | Open
ABP adding ads | Done
Newshunter P1 banners | Done
Google Plus add new banners | Done
Apache reinstallation? | Open | What is issue with old version?

## Targets
Ad Server Performance issue
Ad Server campaign serving consistency
Cool Ads
Targetting (Location based)
Fetch understanding, resp.
Fetch refactoring
Newshunt refactoring items
User Profiling
Sept:
1. Ad server campaign delivery predictability analysis:
a. This would be ongoing activity for campaigns during Jul.
b. Will try to add more tools for easier monitoring & debugging.
c. Will keep updating the ‘configuration guidelines’ for better predictability.
2. Load balanced setup implementation
3. Location based targeting:
a. Identifying the vendor for cellid/Lat/Long to location mapping service.
b. Design for ‘location lookup, location based delivery limitation configuration (city, region, country, locality)’.
c. Implementation of ‘city based’ targeting for clients reporting lat/long.
d. TODO:
i. Whole implementation may not finish by end of Jul due to 2nd item taking most of time.
ii. Rest implementation items will have to be carried in August.
4. User profiling:
a. Definition for the user profiling requirement.
b. One pager on the design.
5. Soft commit:
a. Fetch: remodeling of newsitem for publish/update date.